## Sheet1
Gantt Charts
Isaac A. Rivera
Yadiel Camacho |  | Project Start: | 2022-11-11
|  | Display Week: | 1 |  | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19
Original Project Plan | time axis 2022-11-07 to 2022-12-25
Task | Assigned To | Progress | Start | End | time axis 2022-11-07 to 2022-12-25
ESP32 Functions
Support Calibration of the thermistors | Yadiel Camacho | 100% | 2022-11-11 | 2022-11-13
Connect to the wifi | Isaac A Rivera | 100% | 2022-11-13 | 2022-11-16
Connect to the cloud server | Isaac A Rivera | 100% | 2022-11-16 | 2022-11-21
Can get information about the room and location | Isaac A Rivera | 100% | 2022-11-21 | 2022-11-24
Configuration support by subscribing to a MQTT topic | Isaac A Rivera | 100% | 2022-11-24 | 2022-12-02
Send the temperature reading to a central server | Isaac A Rivera | 100% | 2022-12-02 | 2022-12-06
Make a LED/LCD display or keypad for better interaction | Isaac A Rivera | 100% | 2022-12-06 | 2022-12-09
Hey Google | Isaac A Rivera | 100% | 2022-12-02 | 2022-12-11
Documentation
Architecture/Design doc | Yadiel Camacho | 100% | 2022-12-01 | 2022-12-03
Project plan (Gantt charts) | Yadiel Camacho | 100% | 2022-12-03 | 2022-12-05
Tools set list | Yadiel Camacho | 100% | 2022-12-03 | 2022-12-04
Readme File | Yadiel Camacho | 100% | 2022-12-05 | 2022-12-08
|  | Project Start: | 2022-11-17
|  | Display Week: | 1 |  | 2022-11-07: 2022-11-07; 2022-11-14: 2022-11-14; 2022-11-21: 2022-11-21; 2022-11-28: 2022-11-28; 2022-12-05: 2022-12-05; 2022-12-12: 2022-12-12; 2022-12-19: 2022-12-19
Actual Project Plan | time axis 2022-11-07 to 2022-12-25
Task | Assigned to | Progress | Start | End | time axis 2022-11-07 to 2022-12-25
ESP32 Functions
Support Calibration of the thermistors | Isaac A Rivera - Yadiel Camacho | 100% | 2022-11-17 | 2022-12-10
Connect to the wifi | Isaac A Rivera | 100% | 2022-11-19 | 2022-11-21
Connect to the cloud server | Isaac A Rivera | 100% | 2022-11-21 | 2022-11-26
Can get information about the room and location | Isaac A Rivera | 20% | 2022-11-26 | 2022-12-11
Configuration support by subscribing to a MQTT topic | Isaac A Rivera | 100% | 2022-11-27 | 2022-12-04
Send the temperature reading to a central server | Isaac A Rivera | 100% | 2022-12-04 | 2022-12-11
Make a LED/LCD display or keypad for better interaction | Isaac A Rivera | 75% | 2022-12-04 | 2022-12-06
Hey Google | Isaac A Rivera | 0% | 2022-12-04 | 2022-12-11
Documentation
Architecture/Design doc | Yadiel Camacho | 100% | 2022-12-01 | 2022-12-11
Project plan (Gantt charts) | Yadiel Camacho | 100% | 2022-12-04 | 2022-12-05
Tools set list | Yadiel Camacho | 100% | 2022-12-04 | 2022-12-05
Readme File | Yadiel Camacho | 100% | 2022-12-05 | 2022-12-08